## Timeline
Phase | Dates | Core Activities | Primary Owner(s)
Project kickoff & data‑source mapping | 1 – 2 Jun | Confirm scope, list public datasets (NFHS‑5, NCRB, NHRC, NGO portals), set up shared repo | All (Suraj facilitates)
Data scraping & ingestion | 3 – 4 Jun | Write/execute web‑scrapers, store raw CSV/JSON | Suraj & Bharti
Data cleaning & preprocessing | 5 – 6 Jun | Handle missing values, standardise codes, create master table | Suraj (lead), Bharti + Omkar
Exploratory data analysis (EDA) | 7 – 9 Jun | Trend charts, heat maps, outlier checks; shortlist key indicators | All (rotating pairs)
Work‑stream kick‑off & task allocation | 10 – 11 Jun | Freeze individual deliverables, draft style guide | All
Design & build – Dashboard (α‑version) | 12 – 15 Jun | Layout, filter logic, GIS layer | Bharti (lead)
Design & build – PPT skeleton | 12 – 15 Jun | Storyboard, slide master, icon set | Omkar (lead)
Design & build – Poster concept | 13 – 17 Jun | Typography, colour palette, A2 mock‑up | Suraj (lead)
Feature integration – Dashboard (β) | 16 – 19 Jun | Interactivity, drill‑downs, export buttons | Bharti
First draft – PPT only | 16 – 19 Jun | Include visuals from EDA, policy highlights | Omkar
First draft – Written report | 18 – 22 Jun | Methodology, findings, lit. review | Suraj
Internal peer review (Cycle 1) | 20 – 22 Jun | Cross‑check accuracy & coherence | All
Revisions & polishing | 23 – 24 Jun | Apply feedback, tighten figures & wording | Respective owners
Final refinements & packaging | 25 – 27 Jun | Consolidate dashboard links, tidy poster, version final deck & report | All (Suraj runs checklist)
Project Completion | 28 Jun | Final sync, archival, optional backup & documentation | All

## Budget Estimation
Item | Unit cost | Qty | Total | Notes
Existing laptops (in‑kind) | 0 | 3 | 0 | Personally owned
Open‑source software (Python, Power BI Community) | 0 | – | 0 | FOSS / free licences
Cloud storage (Google Drive for submission; OneDrive for working data) | 0 | – | 0 | Free tiers
Pro‑bono senior/mentor guidance | 0 | – | 0 | Voluntary support
Grand total |  |  | ₹ 0 | No external funds required

## Stakeholder Responsibility Matr
Deliverable / Task | Suraj (Team lead) | Bharti | Omkar | Senior*
Project charter | A/R | C | C | –
Data scraping & cleaning | R | R | C | –
Exploratory analysis | R | R | R | –
Interactive dashboard (Power BI) | C | A/R | I | C
PPT deck | C | I | A/R | –
Poster design | A/R | I | C | –
Written report | A/R | C | C | –
Quality assurance & peer review | A | R | R | –
Final refinements & packaging | A/R | C | C | –
Legend: A = Accountable, R = Responsible, C = Consulted, I = Informed
* Senior is only consulted on the Power BI dashboard, for working on maps.